## Sheet1
ID | Risk Description | Likelihood of the risk occuring | Consequence of the risk occuring | Risk rating based on severity | Action
1 | Natural Disaster | Rare | Catastrophic | Tolerable | Share/Transfer | Risk Matrix
2 | Bugs/Errors | Likely | Moderate | High | Reduce | Consequence
3 | Security Breaches | Rare | Minor | Very Low | Share/Transfer | Catastrophic | Tolerable | High | Very High | Very High | Very High
4 | Second Covid Lockdown | Possible | Major | High | Accept | Major | Low | Tolerable | High | Very High | Very High
5 | Team member ill and/or withdraws from course | Possible | Major | High | Accept | Moderate | Low | Low | Tolerable | High | High
6 | Data Loss | Unlikely | Minor | Low | Reduce | Minor | Very Low | Low | Tolerable | Tolerable | High
7 | Client closes down | Rare | Catastrophic | Tolerable | Accept | Insignificant | Very Low | Very Low | Low | Tolerable | Tolerable
8 | Client building burns down | Unlikely | Major | Tolerable | Share/Transfer |  | Rare | Unlikely | Possible | Likely | Almost Certain
9 | Economic conditions | Possible | Minor | Tolerable | Accept | Likelihood
10 | Delays | Possible | Moderate | Tolerable | Reduce
11 | Lack of commmunication | Unlikely | Moderate | Low | Reduce | Opportunities
12 | Client withdraws/pulls out | Rare | Catastrophic | Tolerable | Accept | Referrals to other non for profits for future projects
13 | Theft of devices | Unlikely | Minor | Low | Share/Transfer | Reputation gain
14 | SIT server goes down | Unlikely | Minor | Low | Share/Transfer | Experience with new Apps / Platforms / Programs
15 | Cyber attack on SIT | Rare | Minor | Very Low | Share/Transfer | Tutor Referral Letters
16 | Scope Creep | Unlikely | Moderate | Low | Reduce | Client Referral Letters
17 | Lacking required skills | Possible | Minor | Tolerable | Share/Transfer | Learning Experience
18 | No time left | Possible | Moderate | Tolerable | Share/Transfer | New Skills
19 | Disputes - client/group | Unlikely | Moderate | Low | Reduce | Testimonial / Portfolios
20 | Confidentiality Issues | Rare | Major | Low | Avoid