## Sheet1
Communication Matrix | [6 empty] | Escalation Process
Type | Objective | Channel | Frequency | Audience | Owner | Deliverables | Priority | Definition | Authority | Timeframe
Initial Client Meeting | Discuss objectives, design, requirements, deliverables, wants and needs | Face to Face | Once | Project Lead and Client | Project Lead | Site Map, Features, Layouts | 1 | Major Impact to the project. If not resolved will cause significant impact to project progress | Programme Manager | 24Hrs
Initial Team Meeting | Introduction to the team and project, management approach, methodology | Face to Face | Once | Project Team | Project Lead | Project, Management Approach, Methodology | 2 | Medium Impact to the project. If not resolved may cause reasonable impact to project progress | Programme Manager or Project Lead | 48Hrs
Project Team Meeting | Review Status of the project and complete relevant tasks | Face to face | Weekly | Project Team | Project Lead | Agenda, Minutes, Schedule | 3 | Minor Impact to the project. If not resolved may cause minor impact to project progress | Project Lead | 3-4 Days
Develepment Team Meeting | Complete Develepment tasks | Face to Face | Weekly | Development Team | Development Team | Agenda, Minutes, Schedule | 4 | Minimal Impact to the project, possibly use a different approach/solution | Project Lead | 1 Week
Update Meeting with Client | Update the client on progress and approve design / development options | Face to Face | When Required | Project Lead and Client | Project Lead | Minutes, Feedback
Meeting with Programme Manager | Discuss Project Progress, any issues with client or team members | Face to Face | When Required | Project Lead and Programme Manager | Project Lead | Minutes, Feedback | Plan for Confidential Information | Project Team will keep information confidential, and sign any required documentation
Status Report | Show the progress of the project, what has been acheived, what hasn't, whats worked and what hasn't | Blackboard | 1) 22 September 2020 2) 27 October 2020 | Project Team and Programme Manager | Project Team | Feedback