## Sheet1
Project Organisational Charts |  | Key R = Responsible for A = Accountable for C = Consulted I = Informed |  |  |  | Resource Calendar
| Programme Manager | Project Lead | Design | Development | Documentation | 15 Week Graph
Requirements Gathering | C | A | R | R | R |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15
Website Design | C | A | R | I | I | Design | 8 Hrs | 8 Hrs | 8 hrs | 8 Hrs | 5 Hrs | 5 Hrs | 3 Hrs | 3 Hrs | 3 Hrs | 3 Hrs | 3 Hrs | 3 Hrs | 3 Hrs | 3 Hrs | 3 Hrs
Graphics |  | A | R | I | I | Development | 3 Hrs | 3 Hrs | 3 Hrs | 3 Hrs | 3 Hrs | 3 Hrs | 5 Hrs | 6 Hrs | 8 Hrs | 8 Hrs | 8 Hrs | 8 Hrs | 8 Hrs | 8 Hrs | 8 Hrs
Content |  | A | R | R | R | Documentation | 3 Hrs | 3 Hrs | 3 Hrs | 3 Hrs | 3 Hrs | 3 Hrs | 3 Hrs | 3 Hrs | 6 Hrs | 6 Hrs | 6 Hrs | 6 Hrs | 6 Hrs | 6 Hrs | 6 Hrs
Coding Design |  | A | I | R | I
Coding Input |  | A | I | R | I | Roles and Responsibilities
Prototype | C | A | I | R | I | Name | Week 1: Role; Week 2: Responsibility
Testing |  | A | R | R | R | Anita Murphy | Week 1: Programme Manager; Week 2: Overseeing the project group, assisting with the learning process, Conflict Resolution, Support, Consultation
Implementation | C | A | R | R | R | Samuel Logan | Week 1: Project Lead, Design; Week 2: The Design Process, Overseeing the project as a whole, Quality Control, Time Management, Conflict Resolution
[6 empty] | Sean Cruickshank | Week 1: Development; Week 2: Development of the website, implementing the database, creating prototypes, testing and implementation
[6 empty] | Ricky Castle | Week 1: Development; Week 2: Development of the website, implementing the database, creating prototypes, testing and implementation
[6 empty] | Scott Delaney | Week 1: Documentation; Week 2: Creating, testing, implementing recipe database, documentation, status reports, final report
Performance Reviews |  | At the end of each phase and at the end of the project
Training Required |  | Any training required will be completed by personal research or lessons with the relevant tutor
Recognition and Rewards |  | Team Recognition and rewards would be a possible reference from the client
How Resources will be acquired |  | Resources willl be acquired as needed on a case by case basis
Timeline for Training / Skill Sets / Resources |  | training timeline would be 1 - 3 weeks depending on the skill level required